## UpdatedRequirementsStack
Requirement ID | Description | Story Points | Priority | Sprint No. | Status | Assigned/Completed By | Additional Notes
1.1 | Create GitHub repository | 1 | 1 | 1 | Completed | Addison |  | Sprint 1 total story points
1.2 | Setup Node and Typescript w/ configs in repository | 1 | 1 | 1 | Completed | Addison |  | Sprint 2 total story points
1.3 | Setup Next.js and React in repository | 1 | 1 | 1 | Completed | Addison |  | Sprint 3 total story points
2.1 | Display entry page | 1 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data | Sprint 4 total story points
2.2 | Display weekly schedule grid and tabs for each semester and each semester plan | 3 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data
2.3 | Make each semester + semester plan combo correspond to a new schedule page | 3 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data | increase the tasks!!
2.4 | Display all schedule combinations for courses for each semester + semester plan | 5 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data
2.5 | Display course search bar to query courses based on course name or course ID | 5 | 1 | 2 | Done | Marco | work with hardcoded data??
2.61 | Display queried course's name, and credit hours | 2 | 1 | 2 | Done | Marco
2.62 | Display additional information in a Pop up menu | 2 | 1 | 2 | Completed | Marco
2.7 | Allow user to add/delete courses from schedule | 3 | 1 | 2 | Done | Marco
2.81 | Display all selected courses to the right of the schedule grid | 3 | 1 | 2 | Completed | Anya
2.82 | add delete button within each course displayed in course list | 2 | 1 | 3 | Completed | Marco
2.9 | Display message if all offerings of selected course conflict with current schedule |  | 2 | 2 | In Progress | Anya
3.1 | Allow schedule to be saved |  | 1 | 3 | Completed | Addison, Elizabeth
3.2 | Allow saved schedule to be edited |  | 1 | 3 | In Progress | Addison
3.3 | Allow schedule to be deleted |  | 1 | 3 | In Progress | Addison
4.1 | Set up database to store course information |  | 1 | 2 | Completed | Hunter
4.2 | Setup database to store users |  | 1 | 2 | Completed | Hunter
4.3 | Setup database to store selected courses for each user |  | 1 | 2 | Completed | Hunter
5 | Add course names, credit hours, and descriptions to database |  | 1 | 2 | Completed | Hunter
6.1 | Account Creation UI | 2 | 2 | 2 | Completed | Janna
6.2 | Account Creation Authentication with Supabase | 3 | 2 | 2 | Completed | Janna
6.3 | Login Page UI | 2 | 2 | 2 | Completed | Janna
6.4 | Login Page Authentication with Supabase | 3 | 2 | 2
6.5 | Account creation and login API routing | 3 | 2 | 2
6.6 | Login credential authentication |  | 2 | 2
6.7 | Frontend login page |  | 2 | 2
7.1 | Password Reset Button | 1 | 3 | 3
7.2 | Password Reset Email Link | 3 | 3 | 3
7.3 | Update Password UI | 1 | 3 | 3
7.4 | Update Password in Supabase | 3 | 3 | 3
8 | Deploy frontend to Vercel |  | 3 | 3
9 | Make the UI fancy |  | 3 | 2
10 | Add CurrentSchedule List to display class sections in current permutation | 3 | 2 | 4 | Completed | Marco
11.1 | Record raw footage For tutorial video | 2 | 2 | 5 | In Progress | Marco
11.2 | Edit Footage for tutorial video | 5 | 2 | 5 | In Progress | Marco