## UpdatedRequirementsStack
Requirement ID | Description | Story Points | Priority | Sprint No. | Status | Assigned/Completed By | Additional Notes
1.1 | Create GitHub repository | 1 | 1 | 1 | Completed | Addison
1.2 | Setup Node and Typescript w/ configs in repository | 1 | 1 | 1 | Completed | Addison
1.3 | Setup Next.js and React in repository | 1 | 1 | 1 | Completed | Addison
2.1 | Display entry page | 1 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data
2.2 | Display weekly schedule grid and tabs for each semester and each semester plan | 3 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data
2.3 | Make each semester + semester plan combo correspond to a new schedule page | 3 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data
2.4 | Display all schedule combinations for courses for each semester + semester plan | 5 | 1 | 1 | Completed | Elizabeth | worked with hardcoded data
2.5 | Display course search bar to query courses based on course name or course ID | 5 | 1 | 2 | Done | Marco | work with hardcoded data??
2.6 | Display queried course's name, credit hours, and additional information in a dropdown menu | 2 | 1 | 2 | Done | Marco
2.7 | Allow user to add/delete courses from schedule |  | 1 | 2 | In Progress | Marco
2.8 | Display all selected courses to the right of the schedule grid (with an add/delete option beside each one?) |  | 1 | 2 | In Progress | Anya
2.9 | Display message if all offerings of selected course conflict with current schedule |  | 2 | 2 | In Progress | Anya
3.1 | Allow schedule to be saved |  | 1 | 2 | In Progress | Addison | work with Supabase
3.2 | Allow saved schedule to be edited |  | 1 | 2 | In Progress | Addison
3.3 | Allow schedule to be deleted |  | 1 | 2 | In Progress | Addison
4.1 | Set up database to store course information |  | 1 | 2 | Completed | Hunter
4.2 | Setup database to store users |  | 1 | 2 | Completed | Hunter
4.3 | Setup database to store selected courses for each user |  | 1 | 2 | In Progress | Hunter
5 | Add course names, credit hours, and descriptions to database |  | 1 | 2 | Completed | Hunter
6.1 | Login credential authentication |  | 2 | 2 | In Progress | Janna
6.2 | Frontend login page |  | 2 | 2 | In Progress | Janna
7 | Deploy frontend to Vercel |  | 3 | 3 | In Progress
8 | Make the UI fancy |  | 3 | 2 | In Progress | Elizabeth

## OldRequirementsStack
Requirement ID | Description | Story Points | Priority | Sprint No. | Assign
1.1 | Create GitHub repository | 1 | 1 | 1
1.2 | Setup Node and Typescript w/ configs in repository | 1 | 1 | 1
1.3 | Setup Next.js and React in repository | 1 | 1 | 1
2.1 | Display course search | 3 | 1 | 2 | Marco
2.2 | Display schedule options of selected courses | 3 | 1 | 1
2.3 | Do not allow conflicting courses in one schedule | 8 | 1 | 1
3.1 | Allow schedule to be saved | 5 | 1 | 2 | Addison
3.2 | Retrieve saved schedules and allow it to be edited | 5 | 1 | 2 | Addison
3.3 | Allow schedule to be deleted | 3 | 1 | 2 | Addison
4.1 | Export KU course data to excel file and copy & paste into Supabase | 1 | 1 | 2 | Hunter
4.2 | Add course names/number to database | 1 | 1 | 2 | Hunter
4.3 | Add course credit hours to database | 1 | 1 | 2 | Hunter
4.4 | Add course description to database | 1 | 1 | 2 | Hunter
5.1 | Setup database to store course information | 5 | 1 | 2 | Hunter
5.2 | Setup database to store users | 5 | 1 | 2 | Hunter
5.3 | Setup database to store selected courses for each user | 5 | 1 | 2 | Hunter
6.1 | Display queried course's name | 3 | 1 | 1 | Marco
6.2 | Display queried course's credit hours | 1 | 1 | 1 | Marco
6.3 | Display queried course's description | 1 | 1 | 1 | Marco
6.4 | Display total credit hours for all selected courses | 3 | 1 | 1 | Marco
6.5 | Add course meeting time options to database | 3 | 1 | 2 | Hunter
6.6 | Display message if queried course is not offered | 1 | 2 | 2 | Anya
6.7 | Display message if all offerings of queried course conflict with current schedule | 5 | 2 | 2 | Anya
7 | Display tabs for different semester plans | 3 | 2 | 1
8.1 | Login Credential Authentication | 5 | 2 | 2 | Janna
8.2 | Frontend Login Page | 5 | 2 | 2 | Janna
9.1 | Deploy frontend to Vercel | 5 | 2 | 3
9.2 | Deploy databases to Supabase or other cloud-based service | 5 | 2 | 3
10.1 | Allow user to select past schedules | 3 | 3 | 3
| Make The UI fancy | 3 | 3 | 2 | Elizabeth