## RequirementsStack
Requirement ID | Description | Story Points | Priority | Sprint No.
1.1 | Create GitHub repository | 1 | 1 | 1
1.2 | Setup Node and Typescript w/ configs in repository | 1 | 1 | 1
1.3 | Setup Next.js and React in repository | 1 | 1 | 1
2.1 | Display course search | 3 | 1 | 1
2.2 | Display schedule options of selected courses | 3 | 1 | 1
2.3 | Do not allow conflicting courses in one schedule | 8 | 1 | 1
3.1 | Allow schedule to be saved | 5 | 1 | 1
3.2 | Retrieve saved schedules and allow it to be edited | 5 | 1 | 1
3.3 | Allow schedule to be deleted | 3 | 1 | 1
4.1 | Parse KU course data into human-readable format | 8 | 1 | 2
4.2 | Add course names/number to database | 1 | 1 | 2
4.3 | Add course credit hours to database | 1 | 1 | 2
4.4 | Add course description to database | 1 | 1 | 2
5.1 | Setup database to store course information | 5 | 1 | 2
5.2 | Setup database to store users | 5 | 1 | 2
5.3 | Setup database to store selected courses for each user | 5 | 1 | 2
6.1 | Display queried course's name | 3 | 1 | 1
6.2 | Display queried course's credit hours | 1 | 1 | 1
6.3 | Display queried course's description | 1 | 1 | 1
6.4 | Display total credit hours for all selected courses | 3 | 1 | 1
6.5 | Add course meeting time options to database | 3 | 1 | 2
6.6 | Display message if queried course is not offered | 1 | 2 | 2
6.7 | Display message if all offerings of queried course conflict with current schedule | 5 | 2 | 2
7 | Display tabs for different semester plans | 3 | 2 | 1
8.1 | Setup user authentication (login/signup) | 5 | 2 | 3
8.2 | Store login information securely | 5 | 2 | 3
9.1 | Deploy frontend to Vercel | 5 | 2 | 3
9.2 | Deploy databases to Supabase or other cloud-based service | 5 | 2 | 3
10.1 | Display page that shows records of past schedules | 3 | 3 | 1
10.2 | Allow user to select past schedules | 3 | 3 | 3