## UpdatedRequirementsStack
Requirement ID | Description | Story Points | Priority | Sprint No.
1.1 | Create GitHub repository | 1 | 1 | 1
1.2 | Setup Node and Typescript w/ configs in repository | 1 | 1 | 1
1.3 | Setup Next.js and React in repository | 1 | 1 | 1
2.1 | Display entry page | 1 | 1 | 1
2.2 | Display weekly schedule grid and tabs for each semester and each semester plan | 3 | 1 | 1
2.3 | Make each semester + semester plan combo correspond to a new schedule page | 3 | 1 | 1
2.4 | Display all schedule combinations for courses for each semester + semester plan | 5 | 1 | 1
2.5 | Display course search bar to query courses based on course name or course ID | 5 | 1 | 2
2.61 | Display queried course's name, and credit hours | 2 | 1 | 2
2.62 | Display additional information in a Pop up menu | 2 | 1 | 2
2.7 | Allow user to add/delete courses from schedule | 3 | 1 | 2
2.81 | Display all selected courses to the right of the schedule grid | 3 | 1 | 2
2.82 | add delete button within each course displayed in course list | 2 | 1 | 3
2.9 | Display message if all offerings of selected course conflict with current schedule | 3 | 2 | 2
3.1 | Allow schedule to be saved | 5 | 1 | 3
3.2 | Allow saved schedule to be edited | 5 | 1 | 3
3.3 | Allow schedule to be deleted | 5 | 1 | 3
4.1 | Set up database to store course information | 3 | 1 | 2
4.2 | Setup database to store users | 3 | 1 | 2
4.3 | Setup database to store selected courses for each user | 3 | 1 | 2
5 | Add course names, credit hours, and descriptions to database | 2 | 1 | 2
6.1 | Account Creation UI | 2 | 2 | 2
6.2 | Account Creation Authentication with Supabase | 3 | 2 | 2
6.3 | Login Page UI | 2 | 2 | 2
6.4 | Login Page Authentication with Supabase | 3 | 2 | 2
6.5 | Account creation and login API routing | 3 | 2 | 2
6.6 | Login credential authentication | 3 | 2 | 2
6.7 | Frontend login page | 3 | 2 | 2
7.1 | Password Reset Button | 1 | 3 | 3
7.2 | Password Reset Email Link | 3 | 3 | 3
7.3 | Update Password UI | 1 | 3 | 3
7.4 | Update Password in Supabase | 3 | 3 | 3
8 | Deploy frontend to Vercel | 3 | 3 | 3
9 | Make the UI fancy | 1 | 3 | 2
10 | Add CurrentSchedule List to display class sections in current permutation | 3 | 2 | 4
11.1 | Record raw footage For tutorial video | 2 | 2 | 5
11.2 | Edit Footage for tutorial video | 5 | 2 | 5